## Issues Report
Title | Description | Issue ID | State | Assignee | Created At | Due Date | Milestone | Labels | Functions/Screens
Edit user profile | users go to edit user profile, can't update new avatar | 1 | Closed | DieuTQ | 2023-05-24 | 2023-05-31 | iter1 | Task, Done | User profile
send mail | When performing the new account registration function, the system cannot send the confirmation email to the user | 2 | Closed | KietHT | 2023-05-25 | 2023-06-02 | iter1 | Task, Done | User Register
Add product photos | When adding a new product, the user with the marketing role can't add an image for the product section | 3 | Closed | KietHT | 2023-06-01 | 2023-06-11 | iter2 | Task, Done | Add product
Online payment | Can't link online payment function when buying | 4 | Closed | KietHT | 2023-06-03 | 2023-06-14 | iter2 | Task, Done | Cart Completion
Update quantity and price | Update the quantity and price in the cart when making a product purchase | 5 | Closed | TruongBQ | 2023-06-20 | 2023-06-29 | iter3 | Defect, Done | Cart Details
send mail | The system has not been able to send the verification email when the user forgets the password and wants to recover | 6 | Closed | TungDT | 2023-05-23 | 2023-06-01 | iter1 | Task, Done | User Login
Insert pictures into posts | use ckfinder and ckeditor libraries to insert images into articles | 7 | Open | DieuTQ | 2023-06-20 |  | inter3 | Task, Doing | Add posts
Authorization | having problems authorization many different roles | 8 | Closed | LamDT | 2023-06-02 | 2023-06-10 | inter2 | Task, Done | User Authorization
use mysql | The team members have to familiarize themselves with MySQL from scratch, which causes a time loss during the initial phase. | 9 | Closed | All member | 2023-05-14 | 2023-05-18 | iter1 | Done
use gitlab | having problems pushing code merge code, because I'm not used to it | 10 | Closed | All member | 2023-05-18 | 2023-05-25 | iter1 | Done