## Project
Total Project Tracking
Information in the columns A-E are filled in the project initiation; columns F-J to be filled by the end of each development iteration
# | Screen/Function | Feature | Actor | Screen/Function Description | In Charge | Status | Actual | Updated | Update Details
1 | User Login | Common | User | This is a pop-up screen which allows the user to enter email & password to login; on this page, there are also options for user to register new information or reset the password for the case s/he forget it |  | Done | iter1 | none
2 | User Register | Common | User | This is a pop-up screen which allows the user to register himself/herself to the system by inputing following information: full name, gender, email, mobile, and address; User then need to verify by clicking the link sent via email to him/her before being able to access the system |  | Done | iter1 | none
3 | Reset Password | Common | User | The user to input his/her email to receive the reset password link. This link is sent to the user's email for his/her password resetting. - On clicking the link, the user is redirected to the password resetting page in which s/he input new password (twice) for the system access - Note that the link is only available for a specific time duration as configured in the system config file. |  | Done | iter1 | none
4 | Change Password | Common | User | This is a pop-up screen which allows the user to change his/her password by inputting his current password as well as new password (twice) |  | Done | iter1 | none
5 | User Profile | Common | User | This is a pop-up screen which allows the user to edit his/her profile information, including the registered ones & the avatar image. Please note that s/he is not allowed to change the email |  | Done | iter1 | none | inserrt img user
6 | Home Page | Public | User | Show sliders, hot posts, featured products + the slider with the latest posts, static contacts/links - Shown slider information includes its image and title; the user is redirected to the slider's backlink on his/her clicking - Shown post information includes its thumbnail, title, brief-info; the user is redirected to the post's details on his/her clicking - Shown product information includes its thumbnail, title, brief information; the user is redirected to the product's details on his/her clicking |  | Done | iter1 | none
7 | Blogs List | Public |  | Show the posts paginatedly (sorted by updated date, paginated) + the sider with the post search box, post categories, the latest posts, and static contacts/links; Shown post information includes its thumbnail, title, brief-info; the user is redirected to the post's details on his/her clicking |  | Done | iter1
8 | Blog Details | Public | User | Show post details (including title, author, updated date, category, and post details) + the sider with the post search box, post categories, static contacts/links |  | Done | iter2 | none
9 | Products List | Public | User | Show product details (including title, category, images, original price, sale price, and product details) + the sider with the product search box, product categories, the latest products, and static contacts/links |  | Done | iter1 | none
10 | Cart Details | Public | User | Show the cart details with list of the user's chosen products (including Id, title, price, quantity, total cost) and the total order price + the sider with the product search box, product categories, the latest products, and static contacts/links; The user can - Change the quantity of each product: the total cost is automatically adjusted - Choose to delete/remove product by clicking on the deleting icon - Click the Choose More Product button to go to Products List page - Click the Check Out button to go to the Cart Contact page Please notes: the user's chosen products from the last browsing session are remained in his/her cart until s/he submit the cart. However, the product prices are updated with the latest prices in the system |  | Done | iter2 | iter3
11 | Product Details | Public | User | Show product details (including title, category, images, original price, sale price, and product details) + the sider with the product search box, product categories, the latest products, and static contacts/links |  | Done | iter1 | none
12 | Cart Contact | Public | User | Show the list of user chosen product (including id, title, price, quantity, total cost), the total order price and the receiver information (including full-name, gender, email, mobile, address, notes) for user to edit/input + the sider with the product search box, product categories, the latest products, and static contacts/links - In case the user has logged in, the receiver information would be filled with the user's information- The user can click the Change button to come back to the Cart Details page for changing the choosing products, click the Submit button to submit the order before redirecting user to the Card Completion or Error page (due to technical error or any out-of-stock product) |  | Done | iter2 | none
13 | Cart Completion | Public | User | This page show the cart completion notes + the sider with the product search box, product categories, the latest products, and static contacts/links; Before this page is shown: - The Order status is changed to submitted; - The product's available quantities are updated accordingly - The submitted order is assigned automatically to the active salers rotatedly - If the receiver information (name, email, mobile, gender) is new or changed (checking via the email0, the latest receiver information is stored in the system as latest & historical system contact information (for the marketing's reference later) - The customer/user would be received the order confirmation & payment guides via his/her email. Those information is shown on the page also. The payment information (banking account,...) are taken from the system configuration file |  | To Do | iter2 | none
14 | Feedback | Public | User | On receiving the bought products successfully, the receiver would receive a confirmation email with the guides to feedback on each of the received product; Beside, the user/receive could also give the feedback (on a specific product or general feedback) via the website; The user also call this screen from the system menu on the header; The feedback information includes contact information (full name, gender, email, mobile), rated star, the attached images and the contact's free-format feedback The page sider is also shown with the product search box, product categories, static contacts/links; |  | Done | iter1 | iter3
15 | User Authorization | Common | User | Implementation of authorization mechanism in the system, including the specify the role of logged-in user, his/her authorized page links (building the displayed menu items (in the front end) and preventing unauthorized access via enter the links directly) |  | Done | iter2 | none
16 | My Orders | Customer | User | Show the list of user's orders paginatedly + the sider with the product search box, product categories, the latest products, and static contacts/links - Each order include below information: id, ordered date, product (first product name & number of other products if any), total cost, status; - On clicking the link under the order id, user would be redirected to the Order Information page |  | Done | iter2 | none
17 | Order Information | Customer | User | Show the order details, including the information as below + the sider with the product search box, product categories, the latest products, and static contacts/links - The order id, order date, total cost, status - The receiver information: full name, gendar, email, mobile - This list of ordered products, each product include following information & the links/buttons that allow the user to re-buy or feedback: thumbnail, name, category, unit price, quantity, total cost For the submitted orders, the user can choose to update (redirect the user to the Cart Details page for that) or cancel the order |  | Done | iter2 | none
18 | MKT Dashboard | Marketing | User | Show statistics of posts, products, customers, feedbacks & the trend of new customers by day for the last 7 days (the start date & end date can be adjustable) |  | Done | iter2 | none
19 | Posts List | Marketing | User | Show the paginated list of posts (include posts' id, thumbnail, title, category, author, featured, and status information): - The user can filter the post by category, author, status or search by title - Sortable by title, category, author, featured, or status - From each post, the user can choose to hide, show, view, edit it - The page also have the button/link that allows the user to add new post |  | Done | iter3 | none
20 | Post Details | Marketing | User | Show detailed post information (thumbnail, category, title, brief information, description, flag to turn the featurning on/off, status), from that allow the user to input, view or edit them |  | Doing | iter3 | none
21 | Sliders List | Marketing | User | Show the paginated list of sliders (including sliders' id, title, image, backlink, status) - The user can filter the sliders by the status + search by title or backlink - For each slider, the user can choose to hide, show, edit it |  | Done | iter2 | none
22 | Slider Details | Marketing | User | Show detailed slider information (image, title, backlink, status, notes) |  | Done | iter3 | none
23 | Products List | Marketing | User | Show the paginated list of products (include products' id, thumbnail, title, category, list price, sale price, featured, and status information): - The user can filter the product by category, status or search by title, brief info - Sortable by title, category, list price, sale price, featured, or status - From each product, the user can choose to hide, show, view, edit it - The page also have the button/link that allows the user to add new product |  | Done | iter2 | none
24 | Product Details | Marketing | User | Show detailed product information (thumbnail, category, title, brief information, attached images, description, quantity, list price, sale price, flag to turn the featurning on/off, status), from that allow the user to input, view or edit them |  | Done | iter3 | none
25 | Customers List | Marketing | User | Show the list of customers / contacts paginatedly (include contacts' id, full name, gender, email, mobile, status): - The user can filter the customers by status + search by full name, email, mobile - Sortable by full name, email, mobile, status - From each customer, the user can choose to add new, view or edit it |  | To Do | iter2 | none
26 | Customer Details | Marketing | User | Show detailed customer/contact information (full name, gender, email, mobile, address, status), from that allow the user to input, view or edit them (excep for the status which is generated automatically - contact, potential or customer) Besides, the screen also shows the list of customer/contact changes history in the form of a table which includes following columns: email, full-name, gender, mobile, address, updated by, updated date |  | To Do | iter2 | none
27 | Feedbacks List | Marketing | User | Show the list of feedbacks paginatedly (include feedbacks' contact full name, product name, rated star, status): - The user can filter the feedbacks by status, product, rated star + search by full name, feedback content - Sortable by full name, product name, rated star, status - From each feedback, the user can choose to view or change it's status |  | Done | iter3 | none
28 | Feedback Details | Marketing | User | Show the feedback details (contact full name, email, mobile, product, rated star, feedback, images status) from that allow the user to change its status |  | Done | iter3 | none
29 | Orders List | Sale | User | Show the list of orders paginatedly - The list can be shorted by the order date, customer name, total cost, status - Each order include below information: id, ordered date, customer name, product (first product name & number of other products if any), total cost, status; - Allow the users to filter the order by the order date (from, to), sale name, status - Allow the user to search the orders by order id, customer name - On clicking the link under the order id, user would be redirected to the Order Details page |  | Done | iter3 | none
30 | Order Details | Sale | User | Show the order details, including the following information: - Basic order information: order id, customer full name, email, mobile, order date, total cost, sale name, status - The receiver information: full name, gendar, email, mobile, address - This list of ordered products, each product include following information: thumbnail, name, category, unit price, quantity, total cost Sale Manager & the assigned Sale can change the order status & the sale notes Sale Manager can assign the order to other sale |  | Done | iter3 | none
31 | Sale Dashboard | Sale | User | Show the trend of success/total orders, and the revenues trends by day for the last 7 days for all or a specific sale person (the start date, end date, sale, order status can be adjustable) |  | To Do | iter3 | none
32 | Admin Dashboard | Admin | User | Show statistics of new orders (success, cancelled, submitted), revenues (total, by product categories), customers (newly registered, newly bought), feedbacks (average star: total, by product categories) & the trend of order counts (success, all) by day for the last 7 days (the start date & end date can be adjustable) |  | Done | iter3 | none
33 | Users List | Admin | User | Show the paginated list of registered users (include users' id, full name, gender, email, mobile, role, status): - The admin can filter the users by gender, role, status - Allow the admin to seach users by full name, email, mobile - The list is sortable by id, fullname, gender, email, mobile, role, status - From each user, the admin can choose to view or edit it - The page also have the button/link that allows the admin to add new user |  | To Do | iter2 | none
34 | User Details | Admin | User | Show detailed user information (avatar, full name, gender, email, mobile, role, address, status), from that allow the user to add new, view or edit user information - After adding, new generated login password would be email to the new user - The admin can only edit/update the role and status of the user |  | To Do | iter2 | none
35 | Settings List | Admin | User | Show the paginated list of settings (include settings' id, type, value, order, status): - The admin can filter the setting by type, status - Allow the admin to seach settings by value - The list is sortable by id, type, value, order, status - From each setting, the admin can choose to view, activate/deactivate, or edit it - The page also have the button/link that allows the admin to add new setting |  | Done | iter3 | none
36 | Setting Details | Admin | User | Show detailed user information (type, value, order, description, status), from that allow the user to add new, view or edit setting information |  | Done | iter3 | none

## Iter1
Iteration Tracking - Iteration 1
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | Level | LOC | SRS | SDS | Notes
1 | User Login | Common | This is a pop-up screen which allows the user to enter email & password to login; on this page, there are also options for user to register new information or reset the password for the case s/he forget it | Lâm | Done | Simple | 60 | II.2.a | II.5
2 | Home Page | Public | Show sliders, hot posts, featured products + the slider with the latest posts, static contacts/links - Shown slider information includes its image and title; the user is redirected to the slider's backlink on his/her clicking - Shown post information includes its thumbnail, title, brief-info; the user is redirected to the post's details on his/her clicking - Shown product information includes its thumbnail, title, brief information; the user is redirected to the product's details on his/her clicking | Lâm | Done | Medium | 120 | II.1.a | II.1
3 | Product Details | Public | Show sliders, hot posts, featured products + the slider with the latest posts, static contacts/links - Shown slider information includes its image and title; the user is redirected to the slider's backlink on his/her clicking - Shown post information includes its thumbnail, title, brief-info; the user is redirected to the post's details on his/her clickShow product details (including title, category, images, original price, sale price, and product details) + the sider with the product search box, product categories, the latest products, and static contacts/linksing - Shown product information includes its thumbnail, title, brief information; the user is redirected to the product's details on his/her clicking | Lâm | Done | Medium | 120 | II.1.e | II.8
4 | Products List | Public | Show the products paginatedly (sorted by updated date) + the sider with the product search box, product categories, the latest products, and static contacts/links; - Shown product information includes its thumbnail, title, brief information, original price, and sale price; - The user is redirected to the product's details on his/her clicking on the product - The user can choose to add the product to the cart or to feedback on the product by clicking the product's Buy & Feedback buttons responsively | kiệt | Done | Complex | 240 | II.1.d | II.2
5 | Blogs List | Public | Show the posts paginatedly (sorted by updated date, paginated) + the sider with the post search box, post categories, the latest posts, and static contacts/links; Shown post information includes its thumbnail, title, brief-info; the user is redirected to the post's details on his/her clicking | Diệu | Done | Simple | 60 | II.1.b | II.10
6 | User Register | Common | This is a pop-up screen which allows the user to register himself/herself to the system by inputing following information: full name, gender, email, mobile, and address; User then need to verify by clicking the link sent via email to him/her before being able to access the system | kiệt | Done | Simple | 60 | II.2.b | II.6
7 | Reset Password | Common | The user to input his/her email to receive the reset password link. This link is sent to the user's email for his/her password resetting. - On clicking the link, the user is redirected to the password resetting page in which s/he input new password (twice) for the system access - Note that the link is only available for a specific time duration as configured in the system config file. | Tùng | Done | Medium | 120 | II.2.c | II.3
8 | Change Password | Common | This is a pop-up screen which allows the user to change his/her password by inputting his current password as well as new password (twice) | Trưởng | Done | Simple | 60 | ll.2.d | ll.4
9 | User Profile | Public | Show the list of user chosen product (including id, title, price, quantity, total cost), the total order price and the receiver information (including full-name, gender, email, mobile, address, notes) for user to edit/input + the sider with the product search box, product categories, the latest products, and static contacts/links - In case the user has logged in, the receiver information would be filled with the user's information- The user can click the Change button to come back to the Cart Details page for changing the choosing products, click the Submit button to submit the order before redirecting user to the Card Completion or Error page (due to technical error or any out-of-stock product)'Show the list of user chosen product (including id, title, price, quantity, total cost), the total order price and the receiver information (including full-name, gender, email, mobile, address, notes) for user to edit/input + the sider with the product search box, product categories, the latest products, and static contacts/links - In case the user has logged in, the receiver information would be filled with the user's information- The user can click the Change button to come back to the Cart Details page for changing the choosing products, click the Submit button to submit the order before redirecting user to the Card Completion or Error page (due to technical error or any out-of-stock product) | Diệu | Done | Simple | 60 | II.2.e | II.7

## Iter2
Iteration Tracking - Iteration 2
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | Level | LOC | SRS | SDS | Notes
1 | User Authorization | Common | Implementation of authorization mechanism in the system, including the specify the role of logged-in user, his/her authorized page links (building the displayed menu items (in the front end) and preventing unauthorized access via enter the links directly) | Lâm | Done | Complex | 240 | II.2.f | II.35
2 | Cart Contact | Public | Show the list of user chosen product (including id, title, price, quantity, total cost), the total order price and the receiver information (including full-name, gender, email, mobile, address, notes) for user to edit/input + the sider with the product search box, product categories, the latest products, and static contacts/links - Ifilled with the user's information- The user can click the Change button to come back to the Cart Details page for changing the choosing n case the user has logged in, the receiver information would be products, click the Submit button to submit the order before redirecting user to the Card Completion or Error page (due to technical error or any out-of-stock product) | Trưởng | Done | Medium | 120 | II.1.h | II.14
3 | Cart Details | Public | Show the list of user chosen product (including id, title, price, quantity, total cost), the total order price and the receiver information (including full-name, gender, email, mobile, address, notes) for user to edit/input + the sider with the product search box, product categories, the latest products, and static contacts/links - In case the user has logged in, the receiver information would be filled with the user's information- The user can click the Change button to come back to the Cart Details page for changing the choosing products, click the Submit button to submit the order before redirecting user to the Card Completion or Error page (due to technical error or any out-of-stock product) | Trưởng | Doing | Medium | 120
4 | My Orders | Customer | Show the products paginatedly (sorted by updated date) + the sider with the product search box, product categories, the latest products, and static contacts/links; - Shown product information includes its thumbnail, title, brief information, original price, and sale price; - The user is redirected to the product's details on his/her clicking on the product - The user can choose to add the product to the cart or to feedback on the product by clicking the product's Buy & Feedback buttons responsively | Tùng | Done | Simple | 60 | II.3.a | II.15
5 | Order Information | Customer | "Show the order details, including the information as below + the sider with the product search box, product categories, the latest products, and static contacts/links - The order id, order date, total cost, status - The receiver information: full name, gendar, email, mobile - This list of ordered products, each product include following information & the links/buttons that allow the user to re-buy or feedback: thumbnail, name, category, unit price, quantity, total cost For the submitted orders, the user can choose to update (redirect the user to the Cart Details page for that) or cancel the order" | Tùng | Done | Medium | 120 | II.3.b | II.16
6 | MKT Dashboard | Marketing | Show statistics of posts, products, customers, feedbacks & the trend of new customers by day for the last 7 days (the start date & end date can be adjustable) | Diệu | Done 90% | Simple | 60
7 | Blog Detail | Public | Show post details (including title, author, updated date, category, and post details) + the sider with the post search box, post categories, static contacts/links | Diệu | Done | Simple | 60 | II. 1.c | II.17
8 | Products List | Marketing | Show the paginated list of products (include products' id, thumbnail, title, category, list price, sale price, featured, and status information): - The user can filter the product by category, status or search by title, brief info - Sortable by title, category, list price, sale price, featured, or status - From each product, the user can choose to hide, show, view, edit it - The page also have the button/link that allows the user to add new product | Kiệt | Done | Medium | 120 | II. 4.b | II.11
9 | MKT Dashboard | Marketing | Show statistics of posts, products, customers, feedbacks & the trend of new customers by day for the last 7 days (the start date & end date can be adjustable) | Diệu | Done | Simple | 60 | II. 4.a | II.18
10 | Sliders List | Marketing | Show the paginated list of sliders (including sliders' id, title, image, backlink, status) - The user can filter the sliders by the status + search by title or backlink - For each slider, the user can choose to hide, show, edit it | Kiệt | Done | Simple | 60 | II. 4.c | II.12
11 | Cart Details | Public | Show the cart details with list of the user's chosen products (including Id, title, price, quantity, total cost) and the total order price + the sider with the product search box, product categories, the latest products, and static contacts/links; The user can - Change the quantity of each product: the total cost is automatically adjusted - Choose to delete/remove product by clicking on the deleting icon - Click the Choose More Product button to go to Products List page - Click the Check Out button to go to the Cart Contact page Please notes: the user's chosen products from the last browsing session are remained in his/her cart until s/he submit the cart. However, the product prices are updated with the latest prices in the system | Trưởng | Done | Medium | Medium | II. 1.g | II.13

## Iter3
Iteration Tracking - Iteration 3
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | LOC | Level | SRS | SDS | Notes
1 | Posts List | Marketing | Show the paginated list of posts (include posts' id, thumbnail, title, category, author, featured, and status information): - The user can filter the post by category, author, status or search by title - Sortable by title, category, author, featured, or status - From each post, the user can choose to hide, show, view, edit it - The page also have the button/link that allows the user to add new post | Diệu | Done | 120 | Medium | II.4.f | II.21
2 | Post Details | Marketing | Show detailed post information (thumbnail, category, title, brief information, description, flag to turn the featurning on/off, status), from that allow the user to input, view or edit them | Diệu | Doing | 120 | Medium | II.4.g | II.22
3 | Sale Dashboard | Sale | Show the trend of success/total orders, and the revenues trends by day for the last 7 days for all or a specific sale person (the start date, end date, sale, order status can be adjustable) | Tùng | Doing | 60 | Simple | II.5.a | II.23
4 | Order Details | Sale | "Show the order details, including the following information: - Basic order information: order id, customer full name, email, mobile, order date, total cost, sale name, status - The receiver information: full name, gendar, email, mobile, address - This list of ordered products, each product include following information: thumbnail, name, category, unit price, quantity, total cost Sale Manager & the assigned Sale can change the order status & the sale notes Sale Manager can assign the order to other sale" | Tùng | Done | 60 | Simple | II.5.c | II.24
5 | Orders List | Sale | "Show the list of orders paginatedly - The list can be shorted by the order date, customer name, total cost, status - Each order include below information: id, ordered date, customer name, product (first product name & number of other products if any), total cost, status; - Allow the users to filter the order by the order date (from, to), sale name, status - Allow the user to search the orders by order id, customer name - On clicking the link under the order id, user would be redirected to the Order Details page" | Tùng | Done | 60 | Simple | II.5.b | II.25
6 | Users List | Admin | "Show the paginated list of registered users (include users' id, full name, gender, email, mobile, role, status): - The admin can filter the users by gender, role, status - Allow the admin to seach users by full name, email, mobile - The list is sortable by id, fullname, gender, email, mobile, role, status - From each user, the admin can choose to view or edit it - The page also have the button/link that allows the admin to add new user" | Tùng | Done | 60 | Simple | II.6.b | II.26
7 | User Details | Admin | "Show detailed user information (avatar, full name, gender, email, mobile, role, address, status), from that allow the user to add new, view or edit user information - After adding, new generated login password would be email to the new user - The admin can only edit/update the role and status of the user" | Tùng | Done | 60 | Simple | II.6.c | II.27
8 | Feedback | Public | On receiving the bought products successfully, the receiver would receive a confirmation email with the guides to feedback on each of the received product; Beside, the user/receive could also give the feedback (on a specific product or general feedback) via the website; The user also call this screen from the system menu on the header; The feedback information includes contact information (full name, gender, email, mobile), rated star, the attached images and the contact's free-format feedback The page sider is also shown with the product search box, product categories, static contacts/links; | Trưởng | Done | 120 | Medium | II.1.f | II.9
9 | Admin Dashboard | Admin | Show statistics of new orders (success, cancelled, submitted), revenues (total, by product categories), customers (newly registered, newly bought), feedbacks (average star: total, by product categories) & the trend of order counts (success, all) by day for the last 7 days (the start date & end date can be adjustable) | Lâm | Done | 60 | Simple | II.6.a | II.30
10 | Settings List | Admin | Show the paginated list of settings (include settings' id, type, value, order, status): - The admin can filter the setting by type, status - Allow the admin to seach settings by value - The list is sortable by id, type, value, order, status - From each setting, the admin can choose to view, activate/deactivate, or edit it - The page also have the button/link that allows the admin to add new setting | Lâm | Done | 60 | Simple | II.4.d | II.28
11 | Setting Details | Admin | Show statistics of new orders (success, cancelled, submitted), revenues (total, by product categories), customers (newly registered, newly bought), feedbacks (average star: total, by product categories) & the trend of order counts (success, all) by day for the last 7 days (the start date & end date can be adjustable) | Lâm | Done | 60 | Simple | II.6.e | II.29
12 | Products Detail | Marketing | Show detailed product information (thumbnail, category, title, brief information, attached images, description, quantity, list price, sale price, flag to turn the featurning on/off, status), from that allow the user to input, view or edit them | Kiệt | Done | 120 | Simple | II.4.d | II.19
13 | Slider Details | Marketing | Show detailed slider information (image, title, backlink, status, notes) | Kiệt | Done | 60 | Simple | II.4.e | II.20
14 | Customers List | Marketing | Show the list of customers / contacts paginatedly (include contacts' id, full name, gender, email, mobile, status): - The user can filter the customers by status + search by full name, email, mobile - Sortable by full name, email, mobile, status - From each customer, the user can choose to add new, view or edit it | Diệu | To Do | 60 | Simple | II.4.k | II.33
15 | Customer Details | Marketing | Show statistics of new orders (success, cancelled, submitted), revenues (total, by product categories), customers (newly registered, newly bought), feedbacks (average star: total, by product categories) & the trend of order counts (success, all) by day for the last 7 days (the start date & end date can be adjustable) | Diệu | To Do | 60 | Simple | II.4.l | II.34
16 | Feedback List | Marketing | Show the list of feedbacks paginatedly (include feedbacks' contact full name, product name, rated star, status): - The user can filter the feedbacks by status, product, rated star + search by full name, feedback content - Sortable by full name, product name, rated star, status - From each feedback, the user can choose to view or change it's status | Trưởng | Done | 120 | Medium | II.4.g | II.31
17 | Feedback Details | Marketing | Show the feedback details (contact full name, email, mobile, product, rated star, feedback, images status) from that allow the user to change its status | Trưởng | Done | 120 | Medium | II.4.j | II.32

## Iter4
Iteration Tracking - Iteration 4
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | Screen/Function Name1 | Feature Name1 | This is short descripiton for the screen/function (2-3 sentences) | Tuấn Hà | Done | II.3 | III.5
2 | Screen/Function Name2 | Feature Name1 | This is short descripiton for the screen/function (2-3 sentences) | Tử Vinh | To Do | II.1 | III.4

## 24 5 2023
ngày 24/5/2023 | Lâm | Kiệt | Tùng | Trưởng | Diệu
Công việc đã hoàn thành | 1.Screen Login - xong 100% 2.Screen Home(đã lầm đc jsp ) | 1: hoàn thành trang register. Jsp | hoàn thành jsp và DAO của forgot password | chưa làm | hoàn thành jsp và DAO
Công việc đang làm | Screen Home(hiển thị data lên Web cả DAO và CONTROLLER) | thích hợp thêm gửi mail đăng kí | làm phần controller | chưa hoàn xong | làm phần up ảnh từ file lên web
Risk/isues |  | thiếu chức năng mail rủi ro làm chậm tiến độ | thiếu chức năng mail rủi ro làm chậm tiến độ |  | thiếu chưc năng up ảnh lên web
Next Plane | Hoàn thành nốt Màn hình home | hoàn thành 100% Register và List Product | hoàn thành 100% Forgot password |  | hoàn thành nôt trang jsp
Actions |  | Tìm hiểu trên mạng hoặc hỏi bạn bè | Tìm hiểu trên mạng hoặc hỏi bạn bè |  | Tìm hiểu trên mạng hoặc hỏi bạn bè

## 26 5 2023
ngày 26/5/2023 | Lâm | Kiệt | Tùng | Trưởng | Diệu
Công việc đã hoàn thành | 1.Screen Login - xong 100% 2.Screen Home(đã lầm đc jsp ) | 1: hoàn thành trang register. Jsp | hoàn thành jsp và DAO của forgot password send mail | jsp DAO | hoàn thành jsp và DAO
Công việc đang làm | Screen Home(hiển thị data lên Web and DAO và CONTROLLER) | thích hợp thêm gửi mail đăng kí | link đến change password |  | làm phần up ảnh từ file lên web
Risk/isues |  | thiếu chức năng mail rủi ro làm chậm tiến độ |  |  | thiếu chưc năng up ảnh lên web
Next Plane | Hoàn thành nốt Màn hình home | hoàn thành 100% Register và List Product | hoàn thành 100% Forgot password |  | hoàn thành nôt trang jsp
Actions |  | Tìm hiểu trên mạng hoặc hỏi bạn bè |  |  | Tìm hiểu trên mạng hoặc hỏi bạn bè

## 30 05 2023
ngày 26/5/2023 | Lâm | Kiệt | Tùng | Trưởng | Diệu
Công việc đã hoàn thành | 1.Screen Login - xong 100% 2.Screen Home-xong 100% 3.Screen ProductDetail--xong 100% | 1: hoàn thành trang register -100% 2:ProductList-100% | reset password-100% | change Password -100% form feedback | UserProfiles-99% BlogList-100%
Công việc đang làm | tìm hiểu thêm để làm các function mới | tìm hiểu thêm để làm các function mới | tìm hiểu thêm để làm các function mới | hoàn thành Feedback | Blog Detail
Risk/isues |  |  |  | chưa hiển thị đc vote sao sản phẩm | thiếu chưc năng up ảnh lên web userProfile
Next Plane | tìm hiểu thêm để làm các function mới | tìm hiểu thêm để làm các function mới | tìm hiểu thêm để làm các function mới | hoàn thành Feedback | hoàn thành nôt Blog Detail và up ảnh lên web userProfile
Actions |  |  |  | tìm hiểu thêm or hỏi các bạn | Tìm hiểu trên mạng hoặc hỏi bạn bè

## 02 06 2023
ngày 02/6/2023 | Lâm | Kiệt | Tùng | Trưởng | Diệu
Công việc đã hoàn thành
Công việc đang làm | User Authorization | Slide list , product list of MKT | My order and Order Information | Cart Detail and Cart contact | Blog detail and Maketting Destboar
Risk/isues
Next Plane
Actions
LOC | 240 | 60+120 | 60+120 | 120+120 | 60+60